## test_case
TEST CASE PROJECT
| Project Name | Swag Labs | Test Case Author | Susmoy | Total Pass | 7
| Module Name | Login, cart add,place_order | Developers Name | Unknown | Total Fail | 4
| Description | Demo Product | Test Case Version | V1 | Total Pause | 0
| Peoject Manager | Sabbir ahmad | Test Execution Start Date | 2025-11-21 | Total Reject | 0
| Browser | Update Chrome | Test Execution Start Date | 0:28 | Total Test Case | 11
Test Case ID | Test Title | Test Description | Pre-conditions | Test Steps | Input Data | Expected Results | Actual Results | Screenshot / Attachments | QA Status | Bug Severity | Bug Priority | Test Type | Date
TC-001 | Verify login with valid username and password | Ensure that entering a valid username and password logs the user into the Home Page successfully without errors | User has a valid account in SauceDemo system; Browser opened; User is on login page. | 1. Open SauceDemo login page 2. Enter valid username 3. Enter valid password 4. Click Login | Username: standard_user Password: secret_sauce | User is redirected to the Home page with inventory items loaded successfully. | Expected Result is properly worked. |  | Pass | High | High | Positive | 2025-11-22
TC-002 | Verify login with valid username and password | Ensure that entering a valid username and password logs the user into the Home Page successfully without errors | User has a valid account in SauceDemo system; Browser opened; User is on login page. | Enter valid username/password 2. Click Login | Username: locked_out_user Password: secret_sauce | User is redirected to the Home page with inventory items loaded successfully. | Epic sadface: Sorry, this user has been locked out.Expected Result not working |  | Fail | High | High | Positive | 2025-11-23
TC-003 | Verify adding a single product to the cart | Ensure user can add one product to the cart successfully | User logged in on home page | 1. Click "Add to cart" for any product 2.Check cart badge 3.Open cart | Click Add to cart botton from product | Cart should show 1 item and product should appear in cart | Expected Result is properly worked. |  | Pass | Critical | High | Positive | 2025-11-22
TC-004 | Remove Item from Cart | Verify removing item updates cart | Item already added to cart list | 1. Go to cart 2. Click Remove 3. Check cart is remove | Click remove botton from cart list | Item removed, badge changes | Successfully Remove Item from Cart |  | Pass | Critical | High | Positive | 2025-11-22
TC-005 | Verify successful checkout information submission | Ensure user can enter valid checkout details and proceed | User is on Checkout Information page | Enter First Name → Enter Last Name → Enter ZIP → Click Continue | First Name: Susmoy Last Name: das Postal Code: 1229 | User should be redirected to Checkout Overview page show pament info,delivary info. | Successful Checkout ,order completes |  | Pass | Critical | High | Positive | 2025-11-23
TC-006 | Verify login with invalid password | Ensure system prevents login when wrong password is used | User has a valid user_name in SauceDemo system; Browser opened; User is on login page. | Enter valid username → Enter invalid password → Click Login | Username:standard_user Password: wrong123 | Error “Username and password do not match” should appear | Successful verify in-valid password show Epic sadface: Username and password do not match any user in this service |  | Pass | High | High | Negative | 2025-11-23
TC-007 | Verify login with empty fields | Ensure login is blocked if username and password are empty | User has Browser opened; User is on login page. | Leave username empty Leave password empty Click Login | N/A | Error “Username is required” should appear | Successful verify show expected result |  | Pass | High | High | Negative | 2025-11-24
TC-008 | Verify accessing inventory page show without login | Ensure system prevents accessing Products page show without authentication | User is not logged in | Open https://www.saucedemo.com/inventory.html URL directly | https://www.saucedemo.com/inventory.html | User must go to direct product page when user are not login the system show product. | User don't go to direct product page when user are not login the system. |  | Fail | High | High | Negative | 2025-11-25
TC-009 | Verify checkout cannot proceed with empty cart | Ensure checkout is blocked when no items are added | User logged in card page,cart is empty | Go to cart Click Checkout | No items | System should prevent moving to checkout information page | Going checkout page and not show any blocked |  | Fail | High | High | Negative | 2025-11-25
TC-010 | Verify checkout with missing first name | Ensure checkout info submission fails without First Name | On Checkout Information page | Leave First Name empty Enter Last Name & ZIP Click Continue | Last Name: Das, ZIP: 1207 | Error message displayed, user cannot continue | Error “First Name is required” successful show expected results |  | Pass | High | High | Negative | 2025-11-25
TC-011 | Verify checkout with invalid ZIP code | Ensure ZIP code field does not accept letters | On Checkout Information page | Enter First Name & Last Name Enter alphabetic ZIP Click Continue | First Name: Susmoy Last Name: Das, ZIP: ABCDE | Validation error should prevent proceeding | Don't show validation error |  | Fail | High | Medium | Negative | 2025-11-25

## Bug_Report
| TEST REPORT |  |  |  | Summary of Report
| Project Name | Swag Labs | Test Case Author | Susmoy das | Total Pass | 7
| Module Name | Login, cart add,place_order | Developers Names | unknown | Total Fail | 4
| Environment | Demo Product | Test Case Version | V1 | Total Pause | 0
| Peoject Manager | Sabbir ahmad | Test Execution Start Date | 2025-11-27 | Total Reject | 0
| Browser | Update Chrome | Test Execution End Date | 2025-11-27 | Total Test Case | 11
SLBug ID | Date | Linked Test Cases | Title | Expected Results | Actual Results | Screenshot /Attachments | QA Status | Bug Severity | Bug Priority | Issue Type | Responsible Dev | QC/Raised BY | Dev Status | Jira Entry | QA Observation | Recommendations
Bug-01 | 2025-11-27 | TC-002 | Verify login with valid username and password | User is redirected to the Home page with inventory items loaded successfully. | Epic sadface: Sorry, this user has been locked out.Expected Result not working |  | Fail | High | High | Positive | unknown | Susmoy | TO DO | Done | The system returns "Epic sadface: Sorry, this user has been locked out." even when valid credentials are used. Expected redirection to the Home page is not happening. Indicates incorrect user status mapping or faulty login validation logic. | Check user account status flags in the authentication database (locked, disabled, active). Verify API response for login request to ensure correct user type is allowed. Re-test with different valid user roles to confirm if issue is isolated to that account.
Bug-02 | 2025-11-27 | TC-008 | Verify accessing inventory page show without login | User must go to direct product page when user are not login the system show product. | User don't go to direct product page when user are not login the system. |  | Fail | High | High | Negative | unknown | Susmoy | Paused | Done | When accessing the Products page without logging in, user should be redirected directly to product view (as per requirement). Actual behavior: System blocks access or does not load product page. Indicates an issue with authentication bypass logic or routing. | Review routing rules and guard logic for the product page. Ensure that “guest access allowed” flag is enabled (if business rule supports it). Add a condition to bypass login check for the inventory page.
Bug-03 | 2025-11-27 | TC-009 | Verify checkout cannot proceed with empty cart | System should prevent moving to checkout information page | Going checkout page and not show any blocked |  | Fail | High | High | Negative | unknown | Susmoy | Paused | Done | System incorrectly allows navigation to checkout information page even when cart is empty. Expected behavior: Block checkout and show validation/error message. This may lead to order submission without items → major functional flaw. | Implement front-end and back-end validation to block checkout when cart quantity = 0. Add user-facing message: “Your cart is empty.” Recheck cart state handling in session/local storage.
Bug-04 | 2025-11-27 | TC-011 | Verify checkout with invalid ZIP code | Validation error should prevent proceeding | Don't show validation error |  | Fail | High | Medium | Negative | unknown | Susmoy | Paused | Done | Invalid ZIP code should trigger validation error and prevent further checkout steps. Actual behavior: No validation error shown, user can proceed. This indicates missing validation rules or broken input validation function. | Add ZIP format validation on user input (front-end + backend). Ensure error messages appear in real-time (UI/UX requirement). Check if ZIP field is incorrectly set as optional.